## 📊 Dashboard
📊 Bug Tracking Dashboard — Digital Kimya
Digital Kimya ITSM Template · digitalkimya.net · MENA & Europe
TOTAL BUGS |  | OPEN |  | IN PROGRESS | RESOLVED |  | CRITICAL / HIGH
14 |  | 6 |  | 4 | 4 |  | 5
In tracker |  | Unresolved |  | Being fixed | Fixed & verified |  | Severity 1 & 2
📋 Bugs by Severity |  |  |  |  | 🗂️ Bugs by Module
Severity | Open | In Progress | Resolved | Total | Module | Count | %
Critical | 1 | 1 | 0 | 2 | Auth / Session | 3 | 21%
High | 2 | 1 | 2 | 5 | Reports | 3 | 21%
Medium | 2 | 2 | 2 | 6 | UI / Frontend | 3 | 21%
Low | 1 | 0 | 0 | 1 | API / Backend | 3 | 21%
[5 empty] | Mobile App | 2 | 14%

## 📋 Bug Tracker
Bug Tracking Register — Digital Kimya Testing Template
© Digital Kimya — digitalkimya.net ¦ ITSM & ITIL Consulting, MENA & Europe
BUG-ID | Reported Date | Bug Title / Description | Severity | Module / Component | Reported By | Assigned Dev | Steps to Reproduce | Status | Fixed in Version
BUG-001 | 2025-01-08 | Login form ignores remember-me checkbox | Medium | Auth / Session | QA Team | Dev-02 | 1. Check remember-me 2. Login 3. Close browser 4. Reopen | Open
BUG-002 | 2025-01-09 | Export to PDF crashes on large datasets > 10k rows | High | Reports | Business User | Dev-05 | 1. Navigate to Reports 2. Select > 10k rows 3. Click Export PDF | In Progress
BUG-003 | 2025-01-10 | Date picker shows wrong year in Arabic locale | Low | UI / i18n | QA Team | Dev-03 | 1. Set locale to AR 2. Open date picker | Resolved | v2.1.4
BUG-004 | 2025-01-11 | API returns 200 on failed payment — no error surfaced | Critical | API / Backend | QA-01 | Dev-01 | 1. Submit payment with invalid card 2. Check response code | In Progress
BUG-005 | 2025-01-12 | Dashboard charts not rendering on Firefox 121 | Medium | UI / Frontend | QA-02 | Dev-04 | 1. Open Firefox 121 2. Navigate to Dashboard | Open
BUG-006 | 2025-01-13 | Session timeout does not redirect to login page | Medium | Auth / Session | QA-01 | Dev-02 | 1. Login 2. Wait 30min idle 3. Try to navigate | Resolved | v2.1.5
BUG-007 | 2025-01-14 | Mobile app crash — Android 14 login screen | High | Mobile App | QA-03 | Dev-06 | 1. Install on Android 14 2. Tap Login | In Progress
BUG-008 | 2025-01-15 | CSV import ignores rows with special characters | Medium | API / Backend | QA Team | Dev-01 | 1. Import CSV with accented names 2. Check imported count | Open
BUG-009 | 2025-01-16 | Notification emails sent twice on ticket creation | High | API / Backend | Business User | Dev-01 | 1. Create ticket 2. Check email inbox | Resolved | v2.1.5
BUG-010 | 2025-01-17 | Search returns results from archived records | Medium | UI / Frontend | QA-02 | Dev-04 | 1. Archive a record 2. Search by name | Open
BUG-011 | 2025-01-18 | Password reset link valid for 72h instead of 24h | High | Auth / Session | Security Review | Dev-02 | 1. Request reset 2. Use link 72h later | Resolved | v2.1.5
BUG-012 | 2025-01-19 | Report scheduler silently fails on empty datasets | Medium | Reports | Ops Team | Dev-05 | 1. Schedule report on empty table 2. Check scheduler log | Open
BUG-013 | 2025-01-20 | iOS app freezes on photo attachment > 8MB | High | Mobile App | QA-03 | Dev-06 | 1. Attach 10MB photo on iOS 2. Tap Submit | Open
BUG-014 | 2025-01-21 | Admin panel accessible to Manager-role users | Critical | Auth / Session | Security Review | Dev-01 | 1. Login as Manager role 2. Navigate to /admin | Open