## 📊 Dashboard
📊 Change Management Dashboard — Digital Kimya
Digital Kimya ITSM Template · digitalkimya.net · MENA & Europe
TOTAL CHANGES |  | PENDING CAB |  | COMPLETED |  | FAILED / ROLLED BACK |  | HIGH RISK
14 |  | 3 |  | 9 |  | 1 |  | 2
This quarter |  | Awaiting approval |  | Successfully deployed |  | Changes reverted |  | Risk score ≥ High
📋 Changes by Type | [5 empty] | 🎯 Changes by Risk
Type | Count | Approved | Completed | Failed |  | Risk Level | Count | %
Normal | 7 | 6 | 5 | 1 |  | Low | 5 | 36%
Standard | 5 | 5 | 4 | 0 |  | Medium | 7 | 50%
Emergency | 2 | 2 | 2 | 0 |  | High | 2 | 14%
📅 Upcoming Change Window — Next 7 Days
CHG-ID | Change Title | Type | Risk | Owner | Window | Status
CHG-0012 | SAP kernel patch 789 | Normal | High | SAP Basis Lead | Sat 01:00–05:00 | CAB Approved
CHG-0013 | Cisco IOS upgrade — Core switch | Normal | High | Network Lead | Sun 02:00–04:00 | Pending CAB
CHG-0014 | Monthly Windows patching | Standard | Low | IT Ops | Sun 01:00–06:00 | Pre-approved

## 📋 Change Register
Change Management Register — Digital Kimya ITSM Template
© Digital Kimya — digitalkimya.net ¦ ITSM & ITIL Consulting, MENA & Europe
CHG-ID | Raised Date | Change Title | Type | Risk | Impact | Change Owner | CAB Approval | Impl. Window | Status | Rollback Plan | Post-Impl. Result
CHG-0001 | 2025-01-08 | Upgrade Apache 2.4 → 2.6 on prod cluster | Normal | Medium | Medium | A. Al-Rashid | Approved | Sat 02:00–04:00 | Completed | Revert to snapshot | Success
CHG-0002 | 2025-01-10 | Apply Windows Server security patches | Standard | Low | Low | IT Ops | Pre-approved | Sun 01:00–05:00 | Completed | Uninstall patches via WSUS | Success
CHG-0003 | 2025-01-14 | Migrate HR module to new DB server | Normal | High | High | B. Leclerc | Approved | Sat 23:00–04:00 | Completed | Restore DB from backup | Success
CHG-0004 | 2025-01-18 | Deploy MFA on VPN gateway | Normal | Medium | High | CISO | Approved | Sun 02:00–05:00 | Completed | Disable MFA policy — revert config | Success
CHG-0005 | 2025-01-20 | Replace core network switch HQ | Normal | High | High | Network Lead | Approved | Sat 22:00–03:00 | Failed | Reconnect old switch — port mapping | Rolled Back
CHG-0006 | 2025-01-22 | Upgrade SAP S/4 to SP 2024.1 | Normal | High | High | SAP Basis | Pending CAB | TBD | Pending | Restore from pre-upgrade snapshot
CHG-0007 | 2025-01-23 | Renew SSL wildcard certificate | Standard | Low | Medium | L2 Security | Pre-approved | Next maintenance window | Completed | Revert to previous cert | Success
CHG-0008 | 2025-01-24 | Enable DMARC enforcement on mail domain | Normal | Medium | Medium | Messaging Lead | Approved | Mon 20:00–22:00 | Completed | Revert to p=quarantine | Success
CHG-0009 | 2025-01-25 | Increase VM RAM — SAP DB server | Standard | Low | Low | Infra Team | Pre-approved | Next maintenance window | Completed | Reduce RAM allocation | Success
CHG-0010 | 2025-01-27 | Deploy new Grafana monitoring node | Normal | Low | Low | Ops Team | Approved | Tue 18:00–20:00 | Completed | Remove node — restore old config | Success
CHG-0011 | 2025-01-28 | Patch Citrix ADC — CVE-2024-XXXX | Emergency | Medium | High | CISO | Emergency approved | Immediate | Completed | Revert patch | Success
CHG-0012 | 2025-01-29 | SAP kernel patch 789 | Normal | High | High | SAP Basis Lead | Approved | Sat 01:00–05:00 | Approved | Restore kernel backup
CHG-0013 | 2025-01-30 | Cisco IOS upgrade — Core switch | Normal | High | High | Network Lead | Pending CAB | Sun 02:00–04:00 | Pending | Revert IOS image from TFTP
CHG-0014 | 2025-01-31 | Monthly Windows patching — batch 2 | Standard | Low | Low | IT Ops | Pre-approved | Sun 01:00–06:00 | Pending | Uninstall patches via WSUS