## 📊 Dashboard
📊 ITIL 4 Implementation Dashboard — Digital Kimya
Digital Kimya ITSM Template · digitalkimya.net · MENA & Europe
TOTAL PRACTICES |  | IN PROGRESS |  | COMPLETED |  | NOT STARTED | AVG MATURITY GAP
10 |  | 2 |  | 0 |  | 8 | +2.1
In scope for rollout |  | Active sprint |  | Fully implemented |  | Scheduled next sprints | Current → Target
📋 Practice Roadmap Overview
ITIL 4 Practice | Phase | Current Maturity | Target | Owner | Status | Target Date
Service Desk | Sprint 1 | Level 2 | Level 4 | IT Ops Mgr | In Progress | 2025-03-31
Incident Management | Sprint 1 | Level 2 | Level 4 | SD Lead | In Progress | 2025-03-31
Service Request Mgmt | Sprint 1 | Level 1 | Level 3 | SD Lead | Not Started | 2025-03-31
Change Enablement | Sprint 2 | Level 2 | Level 4 | Change Mgr | Not Started | 2025-06-30
Service Level Mgmt | Sprint 2 | Level 1 | Level 3 | ITSM Mgr | Not Started | 2025-06-30
Problem Management | Sprint 3 | Level 1 | Level 3 | Problem Mgr | Not Started | 2025-09-30

## 📋 Implementation Tracker
ITIL 4 Implementation Tracker — Digital Kimya ITSM Template
© Digital Kimya — digitalkimya.net ¦ ITSM & ITIL Consulting, MENA & Europe
ITIL 4 Practice | Priority | Practice Owner | Phase | Current Maturity | Target Maturity | Start Date | Target Date | Status | Notes / Blockers
Service Desk | Critical | IT Operations Mgr | Sprint 1 | Level 2 | Level 4 | 2025-01-01 | 2025-03-31 | In Progress | Tool selection finalised — ServiceNow PDI setup
Incident Management | Critical | Service Desk Lead | Sprint 1 | Level 2 | Level 4 | 2025-01-01 | 2025-03-31 | In Progress | Priority matrix agreed with business
Service Request Management | Critical | Service Desk Lead | Sprint 1 | Level 1 | Level 3 | 2025-01-01 | 2025-03-31 | Not Started | Catalogue scoping workshop scheduled Feb
Change Enablement | High | Change Manager | Sprint 2 | Level 2 | Level 4 | 2025-04-01 | 2025-06-30 | Not Started | CAB charter to be drafted
Service Level Management | High | ITSM Manager | Sprint 2 | Level 1 | Level 3 | 2025-04-01 | 2025-06-30 | Not Started | SLA baseline measurement starting Mar
Problem Management | Critical | Problem Manager | Sprint 3 | Level 1 | Level 3 | 2025-07-01 | 2025-09-30 | Not Started | Role not yet assigned — escalation needed
Service Configuration Mgmt | Critical | CMDB Lead | Sprint 3 | Level 1 | Level 4 | 2025-07-01 | 2025-09-30 | Not Started | CMDB scoping — 6 CI classes in scope
Knowledge Management | Medium | Knowledge Lead | Sprint 3 | Level 1 | Level 3 | 2025-07-01 | 2025-09-30 | Not Started
Monitoring & Event Management | High | Infra Lead | Sprint 4 | Level 2 | Level 4 | 2025-10-01 | 2025-12-31 | Not Started | Grafana + ServiceNow integration planned
Continual Improvement | High | ITSM Manager | Sprint 4 | Level 1 | Level 3 | 2025-10-01 | 2025-12-31 | Not Started | CSI register to be created in Q3