## 📊 Dashboard
📊 Problem Management Dashboard — Digital Kimya
Digital Kimya ITSM Template · digitalkimya.net · MENA & Europe
TOTAL PROBLEMS |  | KNOWN ERRORS |  | IN PROGRESS (RCA) |  | RESOLVED | HIGH PRIORITY
8 |  | 3 |  | 3 |  | 2 | 4
In register |  | Workaround available |  | Under investigation |  | Root cause fixed | P1/P2 linked
📋 Problem Register Summary
PRB-ID | Problem Title | Priority | Owner | Status | Linked INC | RCA Status
PRB-0001 | Recurring email delivery failures | High | L3 Infra | Known Error | INC-0001, INC-0008 | Completed
PRB-0002 | SAP login intermittent 502 errors | Medium | SAP Basis | Resolved | INC-0003, INC-0011 | Completed
PRB-0003 | VPN auth failures under load | High | L2 Network | In Progress | INC-0002, INC-0009 | Pending
PRB-0004 | AD sync instability | High | L3 Directory | In Progress | INC-0004, INC-0013 | In Progress

## 📋 Problem Register
Problem Management Register — Digital Kimya ITSM Template
© Digital Kimya — digitalkimya.net ¦ ITSM & ITIL Consulting, MENA & Europe
PRB-ID | Raised | Problem Title | Linked Incidents | Priority | Problem Owner | Root Cause (RCA) | Workaround | Status | Closed Date
PRB-0001 | 2025-01-11 | Recurring email delivery failures | INC-0001, INC-0008 | High | L3 Infra | SMTP relay queue saturation under peak load | Restart relay service manually | Known Error
PRB-0002 | 2025-01-15 | SAP login intermittent 502 errors | INC-0003, INC-0011 | Medium | SAP Basis | Apache worker thread exhaustion | Increase MaxWorkers in httpd.conf | Resolved | 2025-01-20
PRB-0003 | 2025-01-18 | VPN authentication failures under load | INC-0002, INC-0009 | High | L2 Network Team | Under investigation — suspected RADIUS timeout | Increase RADIUS timeout to 10s | In Progress
PRB-0004 | 2025-01-20 | Active Directory sync instability | INC-0004, INC-0013 | High | L3 Directory Services | LDAP connector thread leak under high user volume | Schedule daily connector restart | In Progress
PRB-0005 | 2025-01-22 | File share performance degradation | INC-0012 | Medium | L2 Infra Team | Under investigation | None available | New
PRB-0006 | 2025-01-24 | Mobile app crash — Android 14 | INC-0011 | High | Dev Team | Pending RCA — APK signed with deprecated SHA-1 | Use iOS or web browser | In Progress
PRB-0007 | 2025-01-25 | API gateway latency spikes | INC-0014 | High | L3 Platform | Under investigation | Retry with exponential backoff | New
PRB-0008 | 2025-01-26 | Tape robot offline — backup failures | INC-0016 | Medium | L2 Infra Team | Hardware fault — tape drive head failure | Cloud backup activated as fallback | Known Error