## 📊 Dashboard
📊 IT Risk Register Dashboard — Digital Kimya
Digital Kimya ITSM Template · digitalkimya.net · MENA & Europe
TOTAL RISKS |  | CRITICAL (Score ≥ 15) |  | HIGH (Score 10–14) |  | MITIGATED | OPEN RISKS
12 |  | 2 |  | 4 |  | 6 | 6
In register |  | Immediate action |  | Active monitoring |  | Controls in place | No mitigation yet
🔴 Top Risks by Score
Risk ID | Description | Category | Score | Status | Owner | Mitigation
R-002 | Ransomware attack on endpoints | Security | 15 (CRITICAL) | Open | CISO | EDR + training in progress
R-004 | Loss of key ITSM admin | People | 12 (HIGH) | Open | IT Director | Cross-training plan active
R-001 | Primary DC power failure | Infrastructure | 10 (HIGH) | Mitigated | Infra Mgr | Dual UPS + generator
R-007 | ERP data corruption — month-end | Application | 10 (HIGH) | Open | App Mgr | Snapshot policy review pending

## 📋 Risk Register
IT Risk Register — Digital Kimya ITSM Template
© Digital Kimya — digitalkimya.net ¦ ITSM & ITIL Consulting, MENA & Europe
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Owner | Mitigation Actions | Contingency Plan | Status | Next Review
R-001 | Infrastructure | Primary data centre power failure | 2 | 5 | 10 | Infra Manager | Dual UPS, generator contract | Failover to DR site | Mitigated | 2025-06-30
R-002 | Security | Ransomware attack on endpoints | 3 | 5 | 15 | CISO | EDR deployed, user training quarterly | Restore from immutable backup | Open | 2025-03-31
R-003 | Application | ERP system down during month-end close | 2 | 4 | 8 | App Manager | Dedicated maintenance freeze | Manual processes documented | Mitigated | 2025-06-30
R-004 | People | Loss of key ITSM admin during project | 3 | 4 | 12 | IT Director | Cross-training programme active | Contractor on retainer | Open | 2025-04-30
R-005 | Security | Unpatched CVE on internet-facing systems | 3 | 4 | 12 | CISO | Monthly patch compliance scanning | Emergency patching runbook | Open | 2025-02-28
R-006 | Compliance | GDPR breach — PII data exposure | 2 | 5 | 10 | DPO | Data classification + DLP in place | Breach notification procedure | Mitigated | 2025-06-30
R-007 | Application | ERP data corruption at month-end | 2 | 5 | 10 | App Manager | Pre-close snapshot policy | Point-in-time restore from backup | Open | 2025-03-31
R-008 | Infrastructure | ISP connectivity failure — HQ | 2 | 4 | 8 | Network Lead | Dual ISP active-active | Switch to 4G failover | Mitigated | 2025-06-30
R-009 | People | Phishing attack — credential compromise | 4 | 4 | 16 | CISO | MFA enforced, phishing simulation | Account lockout + IR runbook | Open | 2025-02-28
R-010 | Vendor | Third-party SaaS outage (M365) | 3 | 4 | 12 | IT Director | BCP for M365 outage documented | On-prem fallback for critical email | Open | 2025-06-30
R-011 | Infrastructure | Storage capacity exhaustion on PROD | 3 | 3 | 9 | Infra Manager | Capacity monitoring alerts at 80% | Emergency LUN extension | Mitigated | 2025-04-30
R-012 | Compliance | Audit finding — stale access not removed | 3 | 3 | 9 | IT Manager | Quarterly access review process | Emergency access revocation | Open | 2025-03-31