## 📊 Dashboard
📊 Test Execution Dashboard — Digital Kimya
Digital Kimya ITSM Template · digitalkimya.net · MENA & Europe
TOTAL CASES |  | PASSED |  | FAILED |  | BLOCKED |  | PASS RATE
268 |  | 237 |  | 18 |  | 8 |  | 88.4%
This week |  | Green ✅ |  | Needs fix ❌ |  | Blocked ⛔ |  | Target: ≥ 90%
📋 Test Results by Module — This Week
Week | Module / Feature | Total | Passed | Failed | Blocked | Skipped | Pass Rate | Tester
W02-2025 | Authentication & SSO | 45 | 42 | 2 | 1 | 0 | 93.3% | QA-01
W02-2025 | Incident Management Flow | 38 | 38 | 0 | 0 | 0 | 100% | QA-02
W02-2025 | Report Generation | 22 | 18 | 3 | 0 | 1 | 81.8% | QA-01
W02-2025 | Mobile App – iOS | 30 | 27 | 2 | 1 | 0 | 90% | QA-03

## 📋 Weekly Test Report
Weekly Test Execution Report — Digital Kimya Testing Template
© Digital Kimya — digitalkimya.net ¦ ITSM & ITIL Consulting, MENA & Europe
Week | Module / Feature | Total Cases | Passed | Failed | Blocked | Skipped | Pass Rate % | Tester | Notes
W02-2025 | Authentication & SSO | 45 | 42 | 2 | 1 | 0 | 93.3% | QA-01 | SSO SAML edge case failing
W02-2025 | Incident Management Flow | 38 | 38 | 0 | 0 | 0 | 100% | QA-02 | Full pass
W02-2025 | Report Generation | 22 | 18 | 3 | 0 | 1 | 81.8% | QA-01 | PDF export bug raised BUG-002
W02-2025 | Mobile App – iOS | 30 | 27 | 2 | 1 | 0 | 90% | QA-03 | Blocked on device provisioning
W02-2025 | Change Management Flow | 28 | 26 | 1 | 1 | 0 | 92.9% | QA-02 | CAB approval email not sent
W02-2025 | API Integration Tests | 35 | 30 | 4 | 0 | 1 | 85.7% | QA-04 | BUG-004 blocking payment API
W02-2025 | Mobile App – Android | 30 | 22 | 6 | 2 | 0 | 73.3% | QA-03 | BUG-007 Android 14 crash
W02-2025 | Knowledge Base Module | 20 | 20 | 0 | 0 | 0 | 100% | QA-02 | Full pass
W03-2025 | Authentication & SSO | 45 | 44 | 1 | 0 | 0 | 97.8% | QA-01 | SSO SAML fix verified
W03-2025 | Incident Management Flow | 38 | 37 | 1 | 0 | 0 | 97.4% | QA-02 | Minor UI regression found
W03-2025 | Report Generation | 22 | 20 | 2 | 0 | 0 | 90.9% | QA-01 | BUG-002 partially fixed
W03-2025 | Mobile App – iOS | 30 | 28 | 1 | 1 | 0 | 93.3% | QA-03 | Photo attachment BUG-013 open
W03-2025 | Change Management Flow | 28 | 28 | 0 | 0 | 0 | 100% | QA-02 | CAB email fix verified
W03-2025 | API Integration Tests | 35 | 33 | 2 | 0 | 0 | 94.3% | QA-04 | Payment API partially fixed